# Deep Roots: A Culturally Responsive Agricultural Education Program

Grant Narrative — Fieldstone Foundation Community Development Grant 2026

Submitted by: Piedmont County Cooperative Extension

Program Coordinator: Gloria Mae Wiggins

Version 5 — Near-Final Draft | Last edited: October 3, 2026

# 1. Executive Summary

Deep Roots is a 3-year pilot program designed to deliver culturally responsive agricultural education to small-scale and Black-owned farms across Piedmont County, North Carolina. The program recognizes that traditional Black agrarian knowledge — passed down through generations of Southern farming families — is not merely historical but constitutes a living, adaptive body of practice that has sustained communities through centuries of displacement, dispossession, and institutional neglect.

Housed within the Piedmont County Cooperative Extension and led by Program Coordinator Gloria Mae Wiggins, Deep Roots bridges formal agricultural science with the place-based, experiential knowledge of Piedmont farming communities. The program targets 40 direct participants in its first year, including small-plot holders, beginning farmers, community gardeners, and youth apprentices drawn from historically underserved areas of eastern and southern Piedmont County.

Over the 3-year pilot period, Deep Roots will deliver a six-module soil health workshop curriculum, establish five community trial plots for cover cropping and water conservation research, organize an annual Harvest Day celebration connecting farming practice to cultural heritage, build a participatory evaluation framework rooted in community-defined outcomes, and launch a targeted water rights and conservation initiative addressing infrastructure inequities in eastern Piedmont County.

Total first-year program costs are $71,739.13 in direct expenses, with an indirect cost rate of 15% as permitted by the Fieldstone Foundation. This narrative presents the community context, program design, implementation plan, evaluation strategy, and sustainability vision that together position Deep Roots as a replicable model for culturally grounded agricultural education across the rural South.

# 2. Community Context

Piedmont County sits in the rolling red-clay country of central North Carolina, a landscape shaped as much by human history as by geology. For more than two centuries, Black families have farmed this land — first under enslavement, then as freedpeople navigating the sharecropping system, and today as independent small-plot holders working to preserve both their acreage and the knowledge embedded in it.

## 2.1 Demographics and Agricultural Heritage

According to the most recent USDA Census of Agriculture, Piedmont County contains 1,247 farms, of which 312 (25%) are operated by Black farmers. The median Black-operated farm is 28 acres — less than half the county median of 64 acres — and 71% of Black farm operators are over the age of 55. These figures describe a community at a generational inflection point: without targeted support, decades of accumulated land-based knowledge will be lost as elder farmers retire or pass away without successors prepared to continue their work.

The agricultural heritage of Piedmont County is deeply intertwined with the Gullah/Geechee cultural corridor that stretches from the Carolina coast inland along river systems. Many current farming families trace their horticultural knowledge to Lowcountry foodways — rice cultivation, okra and field pea varieties, sweetgrass traditions, and the herbal medicine practices that sustained Black communities when formal healthcare was inaccessible or hostile. This heritage is not a museum exhibit; it is a living practice that adapts each season to changing soil conditions, weather patterns, and community needs.

## 2.2 Current Challenges

Small and Black-owned farms in Piedmont County face a convergence of challenges that neither market forces nor existing extension programs adequately address:

Land loss and fragmentation: Heirs' property disputes have resulted in the loss of an estimated 8,400 acres of Black-owned farmland in the county over the past three decades. Without clear title, farmers cannot access USDA programs, secure crop insurance, or plan long-term improvements. The Federation of Southern Cooperatives estimates that North Carolina has lost 74% of its Black-operated farms since 1920.

Water access inequity: Eastern Piedmont County farms, disproportionately Black-owned, receive less municipal water infrastructure investment. Many rely on aging wells and unregulated irrigation draws that are increasingly contested as residential development encroaches on agricultural land. Preliminary data from Deep Roots trial plots show significant water savings potential through drip irrigation conversion, with reductions ranging from 28.8% to 32.9% across three pilot farms.

Soil degradation: Decades of conventional row-crop agriculture, followed by periods of abandonment, have left many plots with compacted subsoil, low organic matter, and pH levels below the productive range for common Southern crops. Cover cropping adoption among small holders remains below 15%, compared to 38% for large commercial operations in the county.

Extension access gap: Although Piedmont County Cooperative Extension offers robust programming, participation data reveals that Black farmers attend workshops at roughly one-third the rate of their white counterparts. Community interviews consistently cite three barriers: scheduling conflicts with off-farm employment, distrust rooted in the historical complicity of extension services in discriminatory USDA practices, and a curriculum that does not acknowledge or build upon traditional farming knowledge.

## 2.3 Community Assets

Despite these challenges, Piedmont County possesses significant community assets that Deep Roots is designed to activate and amplify:

A network of elder knowledge keepers — farmers like James Thompson, who manages 40 acres of integrated crop-livestock production off Highway 157 using methods learned from his grandfather, and Bernice Wiggins, whose herbal and sweetgrass knowledge represents an unbroken line of Gullah/Geechee practice. Their participation as workshop facilitators and cultural advisors is central to the program's design.

Institutional support from Piedmont County Cooperative Extension, led by Dr. Patricia Hawkins, who has prioritized equity-focused programming and secured internal resources for culturally responsive curriculum development.

A committed cohort of younger farmers and community organizers who bridge traditional knowledge and modern agricultural science. Existing partnerships with Eastway Middle School, the Durham County Health Department, and the NC Agricultural Lab provide infrastructure for youth engagement, health-related programming, and soil analysis services.

# 3. Program Design

Deep Roots is structured around five interconnected program components, each designed to operate within the 3-year pilot timeframe while building capacity for sustained community ownership beyond the grant period.

## 3.1 Soil Health Workshop Series

The centerpiece of Deep Roots is a six-module soil health workshop curriculum that integrates scientific soil management with traditional Piedmont farming practices. The workshop series will launch with a full-day event on November 7, 2026, at the Piedmont County Extension office, with subsequent sessions held monthly through April 2027.

Module topics include Soil Health Fundamentals (3 hours, led by Gloria Wiggins), Advanced Soil Analysis (4 hours, led by Dr. Hawkins), Soil Health Lab (2 hours, NC Ag Lab staff), Cover Cropping for Piedmont Soils (3 hours, James Thompson), Water Management and Conservation (2 hours, Darnell Washington), and Heritage Seed Saving and Soil Connection (2 hours, Patricia Sawyer and Gloria Wiggins).

Each module combines didactic instruction with hands-on field activities, and every session includes time for participants to share their own observations and practices. Workshop materials will include take-home soil test kits ($12.50 each), heritage seed packets ($3.25 each), and printed curriculum binders ($8.50 each). All materials will be provided at no cost to participants.

## 3.2 Community Trial Plots

Deep Roots will establish and monitor five community trial plots across Piedmont County. Current trial sites include the Henderson farm (plots A-7 eastern field and A-17 western field), Mitchell Road research plots (B-7), the Sawyer farm (B-12), and the Chen terraced hillside (C-3). Each site will receive baseline soil testing, seasonal monitoring, and end-of-season yield data collection.

## 3.3 Harvest Day Celebration

The annual Harvest Day event on October 17, 2026, will be held at the Heritage Oak Community Center — Main Pavilion with an expected attendance of 50+ volunteers and community members. Programming includes harvest demonstrations, seed saving activities, cultural presentations, and a community meal featuring heritage recipes.

## 3.4 Water Rights and Conservation Initiative

The Water Rights and Conservation Initiative documents current water usage, implements drip irrigation conversions, and advocates for equitable infrastructure investment. Water savings data from Henderson (32.5% reduction), Mitchell Road (32.9%), and Sawyer (28.8%) demonstrate the initiative's impact potential.

## 3.5 Evaluation Framework

Deep Roots will implement a three-level participatory evaluation framework: individual (knowledge and practice change), farm-level (soil health and yield metrics), and community-level (participation rates and partnership development). See Appendix A for the complete evaluation instrument and Appendix B for the data collection schedule.

The evaluation design recognizes that not all meaningful outcomes are quantifiable. The program coordinator will maintain narrative field notes documenting qualitative outcomes alongside the quantitative data. A mid-year check-in and end-of-year comprehensive report will be submitted to the Fieldstone Foundation.

# 4. Implementation Timeline

Year 1 (October 2026 – September 2027): Program launch, workshop series delivery, trial plot establishment, Harvest Day, baseline data collection, first-year evaluation.

Year 2 (October 2027 – September 2028): Workshop refinement, expanded trial plots, second Harvest Day, mid-program evaluation, community facilitator training.

Year 3 (October 2028 – September 2029): Community-led workshops, trial plot handoff, third Harvest Day, final evaluation, model dissemination.

Immediate milestones: internal review draft October 14, budget finalization October 14, letters of support October 24, submission October 30.

# 5. Budget Justification

Total first-year direct costs: $71,739.13. Indirect costs at 15%: $10,760.87. Projected total: $82,500.00 (within the Fieldstone Foundation's grant ceiling). See attached budget spreadsheet for complete line-item detail.

The largest line items — Program Coordinator Stipend ($24,000), Curriculum Development ($8,500), and Community Workshop Facilitators ($6,000) — reflect the program's emphasis on human capacity and culturally grounded instruction over equipment and infrastructure.

# 6. Sustainability Plan

Deep Roots transitions to community ownership over the 3-year pilot. Year 3 goals: community facilitators lead workshops, farmers manage trial plots, and a community committee organizes Harvest Day. Piedmont Extension has committed to absorbing the coordinator position contingent on positive evaluation results. Additional funding streams under exploration include the USDA BFRDP, NC Tobacco Trust Fund, and local food cooperative revenue-sharing partnerships.

# 7. Appendices (Referenced)

Appendix A: Evaluation Instruments (pre/post surveys, field data forms)

Appendix B: Data Collection Schedule

Appendix C: Letters of Support (pending — due October 24)

Appendix D: Fieldstone Foundation Grant Guidelines 2026

Appendix E: NC Ag Lab Soil Analysis Report, September 2026