## Harvest Day Planning
Deep Roots Harvest Day — October 17, 2026
Heritage Oak Community Center — Main Pavilion
Category | Item | Assigned To | Status | Count/Quantity | Notes
Volunteers | Total Volunteer Count | Dorothy Mae Jenkins | Confirmed | 47 | Last updated Sept 30 — awaiting final count
Volunteers | Setup crew (morning) | Dorothy Mae Jenkins | Pending | 12 | Need by 7:00 AM
Volunteers | Harvest guides | Gloria Wiggins | Confirmed | 8 | Experienced farmers paired with new participants
Volunteers | Food prep team | Community kitchen committee | Pending | 6 | Heritage recipes — Grandma Bernice advising
Volunteers | Cleanup crew | TBD | Open | 10 | Need to assign lead
Logistics | Tables & chairs | Extension office | Reserved | 20 | Tables; 80 chairs from Heritage Oak
Logistics | Tents/shade | Rental — Johnson Tents | Pending quote | 3 | 10×10 pop-ups for food and registration
Logistics | Portable handwash stations | Durham County Health | Requested | 4 | Required for food service
Logistics | Parking signs | Darnell Washington | Not started | 15 | Directional signs from Highway 157
Food | Main meal — rice, greens, chicken | Community kitchen | Menu set | 60 | Servings — estimate 50 + buffer
Food | Beverages — sweet tea, water | Gloria / store run | Pending | 70 | Cups and coolers needed
Food | Desserts — sweet potato pie | Bernice Wiggins | Confirmed | 8 | Pies from family recipe
Program | Welcome & land acknowledgment | Gloria Wiggins | Draft ready | 1 | 5-minute opening
Program | Harvest demonstration | James Thompson | Confirmed | 1 | 45 minutes — cover crop pull & sweet potato dig
Program | Seed saving station | Patricia Sawyer | Confirmed | 1 | Table with saved seed display
Program | Children's activity | Brandon / Eastway Middle | TBD | 1 | Needs partnership letter first
Safety | First aid kit | Extension office | Available | 2 | Stocked and inspected
Safety | Emergency contacts posted | Gloria Wiggins | Not started | 1 | Print and laminate